## Weekly Summary
Weekly Work Summary — October 5–9, 2026 (mdmpi_mobile_app)
Operational Highlights | Challenge / Issue / Risk | Action Plan
Delivered the Collection Reconciliation Tracker: the new feature was implemented and integrated with case management so reconciliation cases can be tracked through their stages, and the next round of Collection work was scoped in the October 7 to-update list (cart, SI scan, reconciliation stages, and reports). | Reconciliation cases were previously tracked outside the app, making their status invisible to the team and easy to lose between stages. | Test the Reconciliation Tracker with the Collection team against real cases and implement the scoped to-update items (cart, SI scan, reconciliation stages, reports) next.
Shipped releases 1.1.111 and 1.1.112 with Logistics fixes and release-process improvements: the Items page no longer shows another request's items, the Drop Off Receiver field is capped at 255 characters, the app version now shows in Settings and on the login screen, and release announcements were simplified to a short message with the GitHub download link. | Items bleeding between requests risked couriers acting on the wrong cargo, and testers had no easy way to confirm which version they were running. | Verify the Items page fix across request types, and use the visible version number plus the GitHub release link to keep all testers on the latest build.
Cleaned up the Maps integration and release configuration: removed the unused legacy PlacesService, and the CI release pipeline now supplies the Google Maps key to release builds automatically. | Release APKs built by CI were missing the Maps configuration, which showed users a blank map instead of the live tracking view. | Confirm the map renders correctly on each release APK before distribution and keep the release configuration managed through the CI pipeline.