## Weekly Summary
Weekly Work Summary — September 28 – October 2, 2026 (mdmpi_mobile_app)
Operational Highlights | Challenge / Issue / Risk | Action Plan
Built out the Head of Collection experience: a new Team Activity tab gives the Head visibility over collector work, six SMS triggers now notify the Head as plain SMS text on key collection events, Actual Collection displays exactly as the office posts it with targets kept read-only, and the Head admin requirements were documented in the Collection to-do (items 21–24). | The Head of Collection had no live view of field activity and depended on manual reporting, and editable targets risked figures drifting from what the office posted. | Validate the Team Activity tab and the six SMS triggers with the Head of Collection during testing, and implement the remaining Head admin items from the to-do document.
Tightened Collection data correctness and sync feedback: Reconciliation invoices now live only under Reconciliation, For Deposit is recorded as the collector's activity rather than tied to an account, the upload outbox explains why the server rejected a change, money fields format the same way as the Collection web system, and the user directory query (CntmstDao.getAll) gained test coverage. | Misplaced invoices and account-tied deposits distorted per-account figures, and silently rejected uploads left collectors unaware their changes never reached the server. | Reconcile the mobile figures against the Collection web system during testing and monitor the outbox rejection messages to catch recurring server-side validation issues.
Platform housekeeping and configuration: added Collection Settings (Default area, Storage, and About), stopped tracking Android build output in the repository, and logged the week's remaining scope in the Collection to-do document. | Collectors had to re-pick their area on every session, and generated build artifacts were bloating the repository. | Confirm the default-area setting persists across sessions on testers' devices and keep the to-do document as the single tracker for the next round of Collection work.