## Weekly Summary
Weekly Work Summary — October 12–16, 2026 (mdmpi_mobile_app)
Operational Highlights | Challenge / Issue / Risk | Action Plan
Expanded Collection team visibility and reconciliation tracking: the Reconciliation tile now shows the team's pending cases alongside the collector's own, Collected this Month can switch between the collector and all collectors, a Collectors summary is pulled from the /api4 team/summary endpoint (and refuses to show another month's data), reconciliation follow-up reminders were added, a case stage no longer gets stuck after a calendar visit, and the reconciliation stages backend work was completed (Collection item 24 closed). | Collectors and the Head could not see team-wide progress in the app, and a reconciliation case silently stuck in its stage after a calendar visit undermined trust in the tracker. | Validate the team summary figures against the office records with the Head of Collection, and watch the follow-up reminders and stage transitions through a full reconciliation cycle.
Hardened field uploads and data capture: Upload All now sends in batches with progress, resume, and a result banner, a 5 PM reminder prompts collectors to upload their day's work, each saved work item is stamped with the collector's location, Discard All resets the phone to the server's copy, engagement SMS sending was fixed (recipients, delay, and the sending view), and Collection users no longer sit through the Logistics data steps at login. | Large end-of-day uploads could fail midway with no feedback, work was sometimes left un-uploaded overnight, and the backend does not yet store the location fields the phone sends. | Monitor the batched upload and 5 PM reminder with collectors in the field, and follow up on the backend change to store the uploaded location fields.
Shipped releases 1.1.113 and 1.1.114 (merging the Reconciliation Tracker, follow-up reminders, batched upload, and reports via PR #23), planned the Standard Delivery one-scan fill feature, and cleaned the repository by removing the committed weekly summary spreadsheet. | Two same-day releases carrying the large Collection merge increase the chance of a regression reaching collectors. | Gate releases on flutter analyze and the test suite, distribute via the GitHub release link, and start on the Standard Delivery one-scan fill plan next.