## Weekly Summary
Weekly Work Summary — September 1–4, 2026 (mdmpi_mobile_app)
Operational Highlights | Challenge / Issue / Risk | Action Plan
Renamed the Air / Sea service to Air / Sea / Land, adjusted its form validation, and enabled couriers to create Hotline Direct requests. | Renaming a service type touches labels, validation, and routing in several places; a missed spot would show inconsistent naming to users. | Sweep remaining screens and reports for the old Air / Sea label and regression-test the Hotline Direct creation flow as a courier.
Added support for multiple item categories on Pick Up requests. | Existing Pick Up records assume a single category, so the data model and forms had to stay backward-compatible. | Verify old single-category Pick Up records still display and sync correctly after the change.
Enhanced the Release flow: re-assigning driver/helper, validating the assigned crew, and fixing signature clipping on the release form. | Crew re-assignment mid-flow risks releasing with an invalid or incomplete crew; the signature pad was clipping user signatures. | QA the Release flow end-to-end with re-assignments and confirm signatures render fully on printed/exported documents.
Expanded Pull Out handling: added an item list to Pull Out requests, lost-item recording with remarks on completion, a new For Pull Out status between New Request and In Transit, and the ability for couriers to pause an in-transit Pull Out back to For Pull Out. | Introducing a new status into the Pull Out lifecycle risks breaking existing status transitions, filters, and counts across the module. | Regression-test every Pull Out status transition (including pause/resume) and confirm dashboards and list filters count the new status correctly.
Improved Standard Delivery: support for up to 3 proof-of-delivery photos and made recipient name/contact details optional. | Multiple photos increase upload size and sync time on poor mobile connections; optional recipient fields must not weaken delivery accountability. | Monitor photo upload/sync performance in the field and confirm with operations that the relaxed recipient validation matches policy.
Refactored logistics modals for maintainability: decoupled the Pull Out modal behind IPullOutRequestController, extracted the stock receive modal configuration, and enabled dynamic controller injection. | Shared modals were tightly coupled to concrete controllers, making them hard to reuse across request types and risky to change. | Reuse the interface-based modal pattern for the remaining logistics modals and keep DI registrations aligned in GeneralBindings.
Improved perceived performance and UX: form categories now load cache-first with a background refresh, and the redundant success snackbar after list refreshes was removed. | Cache-first loading risks showing stale categories if the background refresh fails silently. | Verify the background refresh updates the cache reliably and surfaces errors through logging when the network is unavailable.
Release management: bumped the app version to 1.1.100+4 and added a post-demo revisions tracking document to keep client feedback organized. | Post-demo feedback items could get lost or duplicated without a single tracking source. | Keep the post-demo revisions document updated as items are completed and use it to drive the next round of releases.