## Weekly Summary
Weekly Work Summary — September 14–18, 2026 (mdmpi_mobile_app)
Operational Highlights | Challenge / Issue / Risk | Action Plan
Set up automated Android CI/CD: a GitHub Actions workflow now builds, signs, and publishes release APKs with dynamic tagging, manual triggers, and environment-based configuration; releases 1.1.105 through 1.1.107 were shipped through it. | Release builds were previously produced manually on one machine, making the process slow, hard to reproduce, and dependent on a single workstation. | Ship all upcoming releases through the automated workflow, monitor the build runs, and refine the release naming and tagging as the cadence grows.
Built the Collection module's offline-first data layer: Collection tables now persist across app upgrades with proper DAOs, the whole workspace downloads in one call, account-level work is saved offline with an upload queue and an Upload All action, and the module now points at the /api4 backend. | Collectors work in the field with unreliable connectivity, so lost or duplicated local data is a real risk — history rows were doubling on every re-download. | Fixed the row doubling and keyed caches on ACCMST client keys; continue field-testing the offline queue and verify uploads reconcile cleanly with the backend.
Planned and executed the Collection data normalization: Stage D (dropping invoice redundancy) was proposed, implemented, and deployed, Stage E1 (web client enrichment screen and client API) was proposed and implemented, and the stages plus C4 verification were documented. | Dropping redundant invoice data on the backend is destructive if the verification is wrong. | Each stage was verified before its backup tables were dropped; keep the stage documents updated as the remaining normalization stages roll out.
Improved payment recording accuracy: fixed money fields that silently changed the amount, made the batch split a single tap instead of manual arithmetic, let a row absorb leftover centavos, and replaced free-typed bank names with a picker from the company bank list that records the bank code. | Silently altered amounts and free-typed bank names produce reconciliation mismatches that are expensive to trace after the fact. | Verified the bank list survives a restart; reconcile recorded amounts and bank codes against the backend during Collection testing.
Overhauled the Collection Bucket: filters aligned with the engagement list (area, due date, amount, sort direction), ordering by account total, ticked accounts rise to the top, redesigned account cards around the balance, and a Filter by Area sheet whose counts match what the filter will show. | The bucket list was slow and janky — due dates were re-parsed on every rebuild, the tap animation stuttered, and an oversized animation asset weighed the screen down. | Cached the parsed dates, re-authored the animation at display size, and made opening the Bucket instant; profile the list again with a full production-size account load.
Gave Collection its own identity and a faster Home: a session-scoped navy theme with matching navigation bar, a dashboard that fits one phone screen without scrolling, summary tiles and Engagement History as looping mirror carousels, and a loading skeleton instead of a blank screen. | Early builds showed a blank Collection home (unbounded stretch rows, a GetX misuse, theme switching mid-build) — a bad first impression for the new module. | All three blank-screen causes were fixed (bounded rows, corrected Obx usage, theme applied after the frame); QA the home screen across small Android phones and Windows desktop.
Streamlined Field Engagement for collectors: the screen now reads like a work queue, the engagement form needs far less typing, deferring picks its reason from a bottom sheet, check fields scroll into view when switched on, and timestamps display as dates instead of ISO strings. | Every extra tap or typed field slows a collector on-site and invites input errors. | Observe collectors using the redesigned flow during testing and keep removing typing in favor of pickers and defaults.
Extended SMS coverage: the collection head is now texted on each recorded collection, and the Air/Sea drop-off text carries the waybill number typed by the courier. | SMS content must stay accurate and complete, since the collection head and clients rely on it as their record of field activity. | Monitor message delivery and content with the collection head during rollout and confirm the waybill appears correctly in drop-off texts.
Tuned Logistics performance and layout: request lists fetch only the selected day instead of everything, Home stops re-downloading all data, the Logistics Home fits one screen with New Request first. | Fetching every request on each visit wasted bandwidth and slowed the Home screen as data grows. | Confirm the day-scoped fetch keeps counts accurate across date changes and apply the same pattern to other heavy lists.