## Weekly Summary
Weekly Work Summary — September 7–11, 2026 (mdmpi_mobile_app)
Operational Highlights | Challenge / Issue / Risk | Action Plan
Rolled out SMS notifications: SMS is now sent on For Delivery with a Message Sent progress screen, and the dispatch time is included in the For Delivery, Air/Sea Dispatch, Pull Out, and Stock Receive In Transit messages. | The telephony plugin did not support Android 11, so SMS sending failed on newer devices. | Vendored and patched the another_telephony plugin for Android 11; monitor SMS delivery success across courier devices in the field.
Strengthened OCR and document references: Part No., Serial No., and PTN are now captured from the Stock Issue Slip, references moved to a full-screen editor with hardened extraction, references made optional for Stock Receive, and references display as grouped chips with Show all / Copy all. | OCR extraction was fragile on real scanned slips, and the Gemini API key was being exposed in the request URL. | Removed the dead backend-OCR path and moved the Gemini key into a request header; continue validating extraction accuracy against real Stock Issue Slips.
Extended Air / Sea / Land requests with a Mode of Shipment dropdown and a new Air / Sea / Land HD (Hotline Direct) form category. | New form categories and fields must stay consistent with existing request filtering, validation, and reporting. | Regression-test Air / Sea / Land request creation across both new categories and confirm downstream lists and SMS handle them correctly.
Fixed dynamic dropdown behavior: validation now works correctly, FormField state stays in sync with the selection, and dropdown validation tests were added. | Dynamic dropdowns could pass validation with stale or empty values, letting bad form data through. | Keep the new dropdown validation tests in the suite and apply the same pattern to remaining dynamic form fields.
Improved live map tracking: replaced the live map drawer with a bottom sheet, removed the placeholder fake vehicles, retired courier markers on delivery completion or request switch, and added tests for the courier marker lifecycle. | Stale courier markers persisted on the map after a delivery finished or the courier switched requests, misleading dispatchers. | Marker lifecycle is now covered by tests; observe live map behavior with real courier movement to confirm markers retire on time.
Polished the delivery UX: proof photos open in a full-screen viewer with swipe/zoom/rotate, the Standard Delivery details page and modal were redesigned for hierarchy, and layouts now render correctly under the Android navigation bar (edge-to-edge, both nav styles). | Edge-to-edge Android rendering caused bottom-anchored widgets to sit under the system navigation bar on gesture and button navigation. | Applied the single-SafeArea inset convention (now documented in CLAUDE.md); verify remaining screens on both gesture and 3-button navigation.
Tightened workflow rules: Dispatch / Drop Off is restricted to the assigned driver or helper, and couriers can backload single items before drop off. | Unassigned crew could act on dispatches, and couriers had no way to handle a partial backload before completing a drop off. | QA the restricted actions with non-assigned accounts and gather courier feedback on the single-item backload flow.
Delivered ISO/QMS documentation: process flow and narrative docs for Collection and Logistics with reference material, plus a docs refresh that pruned delivered plans and rewrote the module READMEs. | ISO/QMS documentation must accurately mirror the implemented app flows or the audit trail loses credibility. | Keep the process-flow docs updated as flows change and complete the remaining items in the post-demo revisions tracker.
Shipped four releases this week: versions 1.1.101, 1.1.102, 1.1.103, and 1.1.104. | A fast release cadence risks shipping regressions if changes are not verified per build. | Continue gating each release on flutter analyze and the test suite, and distribute builds via the shared Drive folder for tester installation.