## Weekly Summary
Weekly Work Summary — September 21–25, 2026 (mdmpi_mobile_app)
Operational Highlights | Challenge / Issue / Risk | Action Plan
Refined the Collection module's financial logic and workflow: Advanced Payments and advance excess now stay as float until applied (with a redesigned Advanced Payment page), For Deposit is excluded from the money totals, CWT and Reconciliation are treated as activities rather than collections with their accounts picked from the client registry, the month's total updates the moment a download lands, invoices can be browsed and filtered by P.O. number, Engagement History gained filters, finished reconciliations fold away, calendar visits are grouped and count only actual collections, and engagements now survive the next sync and land on the correct day. | Misclassified money (advances, deposits, CWT) inflated collection totals and the calendar, and engagement records could be lost or dated wrongly after a sync — both undermine the collection head's reporting. | Walk through the revised totals and float handling with the collection head against real figures, and complete the remaining items in the Collection to-do document (items 9–18, including applying advances).
Improved Logistics data integrity and messaging reliability: Upload Data now lets the user choose what to send, compares each request with the server copy, explains skipped requests and can take the server version; requester and client lookups moved off the retired /api3 endpoint to /api2 with a clear message when a server is dead; Requested By refills itself after an update; and SMS falls back to the Messages app when Android refuses direct sending. | The retired /api3 endpoint served incomplete records and went down for long stretches, and silent upload skips or refused SMS sends left field staff unsure whether their data and messages went through. | Keep the /api2-only boundary enforced (nothing may call /api3 again), monitor Upload Data comparisons during testing, and verify the SMS fallback on devices that block SEND_SMS.
Shipped and maintained the platform: released versions 1.1.108, 1.1.109, and 1.1.110, upgraded core dependencies, showed each department only the settings it uses, standardized app bar styling, fixed label overflow with clearer target progress on Collection, added the modular Claude Code configuration under .claude/ (rules, agents, commands), and cleaned up an empty CI workflow. | Three releases in one week plus core dependency upgrades raise the chance of an unnoticed regression reaching testers. | Gate every release on flutter analyze and the test suite, distribute builds through the shared Drive folder, and log tester feedback in the Collection to-do document for the next cycle.